## Stakeholder Matrix
Stakeholder Analysis
Project Name | Project Description
Migrating to USB-C port | A smartphone company is forced due to new EU law to migrate from micro-usb to USB type-C charging port
Stakeholder | Power (influence of stakeholder) | Interest (impact on stakeholder)
Employees | 2 | 3
Shareholders | 4 | 4
Competitors | 2 | 2
Customers | 5 | 4
Distributors | 4 | 2
Suppliers | 3 | 2
Government | 4 | 1
|  |  |  | High Interest | Low Interest
|  |  | High Power | Customers Shareholders | Government, Distributors, Supliers
|  |  | Low Power | Employees | Competitors

## Concern & Strategies
| Concerns | Strategy
Employees | Concerned about the impact of the migration on their job responsibilities and potential for job loss. | Communicate the migration plan and schedule to employees and provide training and resources to ensure a smooth transition.
Shareholders | Concern about the cost of the migration and the potential impact on the company's bottom line. They may also be concerned about the potential risks and uncertainties associated with the migration. Worry about the company losing its competitive edge if the migration is not executed correctly. | Communicate the potential benefits of the migration and the measures being taken to minimize potential negative impacts on the company's bottom line. Provide regular updates on the progress of the migration and the financial impact on the company. Address any concerns or objections that shareholders may have in a timely and transparent manner.
Competitors | Concern about the company gaining a competitive advantage through the migration. They may also be concerned about the potential for the migration to disrupt the market or create new opportunities. Worry about the migration leading to a change in customer preferences that could negatively impact their own sales. | Monitor the actions and reactions of competitors to the migration and anticipate potential responses. Communicate the company's competitive advantages and how the migration will benefit the company in the long run. Consider partnering with competitors to share information and resources related to the migration, if appropriate.
Customers | Concern about the compatibility of their existing accessories with the new charging ports. They may also be concerned about the availability and cost of adapters. Worry about the migration causing inconvenience or extra expense for them. | Communicate the benefits of the new charging ports and how they will improve the customer's experience. Provide information on how customers can transition to the new charging ports, such as information on adapter options and the compatibility of their existing accessories. Consider offering incentives or discounts to customers to encourage them to switch to the new charging ports. Address any concerns or complaints that customers may have in a timely and responsive manner.
Distributors | Distributors may be concerned about the impact on their existing distribution channels and potential loss of business. | Communicate the migration plan and schedule to suppliers and distributors and work with them to ensure a smooth transition. Address any concerns or complaints that these stakeholders may have in a timely and responsive manner.
Suppliers | Suppliers may be concerned about the impact on their existing contracts and relationships with the company.
Government | Concerned about the safety and performance of the new charging ports and ensuring that the company is meeting all necessary regulations and standards. | Communicate the migration plan and schedule to regulators and ensure that the company is meeting all necessary regulations and standards.